Drilling Schedule – Weekly Snapshot

|  |  |
| --- | --- |
| **Project:** | Earthquake Ready Burnside Bridge |
| **Subject:** | Drilling Activities from August to November 2021 |
| **Date:** | Wednesday, September 08, 2021 |

**Map of all Drilling Locations from August to November**

**Schedule** *(Dates Subject to Change)*

**Week of 9/7**

* B-19 (East – NE 3rd Avenue)
* B-20 (East- Burnside Bridge Approach)
* B-32 (East – American Medical Response)
* B-33 (East – American Medical Response)

**Week of 9/13**

* B-32 (East – American Medical Response)
* B-15 (East - ODOT)
* B-8 (West - Waterfront Park)
* CPT-1 (West - Mercy Corps)
* CPT-2 (West - Mercy Corps)
* CPT-3 (East - ODOT)
* CPT-4 (East - ODOT)
* CPT-5 (East - Pacific Coast Fruit)
* CPT-6 (East - American Medical Response)
* CPT-7 (East - American Medical Response)
* CPT-8 (East – NE 2nd Ave)

**Week of 9/20**

* B-5 (West - Mercy Corps)
* B-6 (West - Mercy Corps)
* B-7 (West – Waterfront Park)
* B-8 (West - Waterfront Park)

**Week of 9/27**

* B-4 (West - Burnside Bridge Approach)
* B-14 (East – ODOT)

**Week of 10/4**

* B-21 (West – NW 1st Ave) – *Note: work will start Sunday night*
* B-22 (West – Naito)

**Week of 10/11**

* B-23 (West – Waterfront Park)

**Week of 10/18**

* No on-land work

**Week 10/25**

* No on-land work

***COMPLETE***

* *B-17 (East - Pacific Coast Fruit)*
* *B-18 (East - Pacific Coast Fruit)*
* *B-16 (East - ODOT)*

**What to Expect**

* All locations are within 375 feet of the bridge.
* This work will require large trucks and drilling equipment to obtain the samples.
* The drilling collects samples that are 8-inches in diameter.
* At each location, contractor activities will occur intermittently and last over the course of one to four days.
* While most of the work will occur during the day, some night work will occur. Noise can vary from the sound of an idling car to a garbage truck.
* Tra­ffic control devices and ‑ flagging will be in place to direct tra­ffic when needed.
* For noise complaints, call 503-988-4884 and the contractor will assist the County to address complaints within 24 hours or before the next scheduled night work.